## Sheet1
TimeSheet Date | Project Name | EmployeeId | Full Name | Task Name | Task Description | SubTask Name | SubTask Description | Hours Spent | Planned Efforts - Task | Actual Efforts - Task | Planned Efforts - SubTask | Actual Efforts - SubTask | SubTask - Start Date | SubTask - Start Date | PlannedEndDate
2017-05-24 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-05-25 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-05-26 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-05-29 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-05-30 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-05-31 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 8 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-06-01 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping- Excess Umbrella Suite | Adhoc Task of 23 DDT scenarios | Revamping-EU LOB-Test Data Update | NULL | 8 | 136 | 82 | 16 | 8 | 2017-06-01 | NULL | 2017-06-07
2017-06-02 | e2 Automation | 15247 | Arpitha Karividha | Revamping - Excess Umbrella Suite | Revamping - Excess Umbrella Suite | Test Data Creation - Excess Umbrella | NULL | 7 | 200 | 109 | 40 | 15 | 2017-06-05 | NULL | 2017-05-16
2017-06-05 | e2 Automation | 15247 | Arpitha Karividha | Revamping - Excess Umbrella Suite | Revamping - Excess Umbrella Suite | Test Data Creation - Excess Umbrella | NULL | 8 | 200 | 109 | 40 | 15 | 2017-06-05 | NULL | 2017-05-16
2017-06-06 | e2 Automation | 15247 | Arpitha Karividha | E2 Revamping-Environmental Suite | E2 Revamping-Environmental Suite DDT | Revamping - ENV LOB- Test Data Creation | Creation, Review and Incorporation of Review Comments | 1 | 420 | 222 | 110 | 50 | 2017-06-02 | NULL | 2017-06-20
2017-07-01 | SmartAid | 8516 | Abhishek Dalal | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | 1 | 30 | 6 | 1 | 1 | 2017-07-01 | NULL | 2017-07-17
2017-07-01 | Support Function QA | 12116 | Suvarna Bodkhe | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | 8 | 8 | 16 | 8 | 16 | 2017-07-01 | NULL | 2017-07-07
2017-07-02 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Bug Verification | Ticket Verification 3.32 | on Staging | 6 | 50 | 43 | 5 | 6 | 2017-07-02 | NULL | 2017-07-03
2017-07-03 | Organisational Level Activities | 8516 | Abhishek Dalal | Meeting | Meeting | Meeting | NULL | 20 | 43750 | 1095 | 43750 | 20 | 2017-07-03 | NULL | 2017-12-31
2017-07-03 | Alexion QA | 11689 | Sagar Saibewar | Santiy Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing | Sanity Testing | 3 | 40 | 3 | 40 | 3 | 2017-07-03 | NULL | 2017-07-07
2017-07-03 | Support Function QA | 12116 | Suvarna Bodkhe | Test Case Design | Test Case Design | Test Case Design | Test Case Design | 8 | 8 | 16 | 8 | 16 | 2017-07-03 | NULL | 2017-07-07
2017-07-03 | Support Function QA | 15247 | Arpitha Karividha | Test Case Execusion | Test Case Execusion | Test Case Execusion | Test Case Execusion | 8 | 8 | 36 | 8 | 36 | 2017-07-03 | NULL | 2017-07-07
2017-07-04 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MAR ETL Mapping document task | Mavis to MAR ETL Mapping document task | Mavis to MAR ETL Mapping document task | Mavis to MAR ETL Mapping document task | 1 | 0 | 1 | 0 | 1 | 2017-07-04 | NULL | 2017-07-07
2017-07-04 | Support Function QA | 12116 | Suvarna Bodkhe | Test Case Execusion | Test Case Execusion | Test Case Execusion | Test Case Execusion | 8 | 8 | 36 | 8 | 36 | 2017-07-04 | NULL | 2017-07-07
2017-07-04 | Support Function QA | 15247 | Arpitha Karividha | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | Defect Retesting and Defect Rasing | 8 | 8 | 16 | 8 | 16 | 2017-07-04 | NULL | 2017-07-07
2017-07-05 | Organisational Level Activities | 12116 | Suvarna Bodkhe | Leaves | Leaves | Sick Leave | NULL | 8 | 40000 | 1699 | 10000 | 8 | 2017-07-05 | NULL | 2017-12-31
2017-07-05 | Support Function QA | 15247 | Arpitha Karividha | Test Case Execusion | Test Case Execusion | Test Case Execusion | Test Case Execusion | 8 | 8 | 36 | 8 | 36 | 2017-07-03 | NULL | 2017-07-07
2017-07-06 | SmartAid | 11303 | Sandesh Upadhye | Ticket Verification | Bug Verification | LUCA and STND | On Dev | 7 | 50 | 43 | 7 | 7 | 2017-07-06 | NULL | 2017-07-03
2017-07-06 | Quality processes | 12116 | Suvarna Bodkhe | Task One | test | suport one | NULL | 8 | 15 | 15 | 5 | 8 | 2017-07-06 | NULL | 2017-06-14
2017-07-06 | Support Function QA | 15247 | Arpitha Karividha | Test Case Execusion | Test Case Execusion | Test Case Execusion | Test Case Execusion | 8 | 8 | 36 | 8 | 36 | 2017-07-03 | NULL | 2017-07-07
2017-07-07 | SmartAid | 8516 | Abhishek Dalal | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | 1 | 30 | 6 | 1 | 1 | 2017-07-07 | NULL | 2017-07-17
2017-07-07 | SmartAid | 8516 | Abhishek Dalal | Test case Design | Test case Design | Update regression Log 7 July, 2017 | Updation of old test cases | 3 | 50 | 22 | 14 | 3 | 2017-07-07 | NULL | 2017-07-03
2017-07-07 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Bug Verification | Smart Aid ticket verification 3.32.2 | NULL | 5 | 50 | 43 | 5 | 11 | 2017-07-07 | NULL | 2017-07-03
2017-07-07 | SmartAid | 11303 | Sandesh Upadhye | Ticket Verification | Bug Verification | Ticket Verification STND 7th July | Ticket Verification STND | 5 | 50 | 43 | 5 | 5 | 2017-07-07 | NULL | 2017-07-03
2017-07-07 | Support Function QA | 12116 | Suvarna Bodkhe | Review and Rework | Review and Rework | Review and Rework | Review and Rework | 7 | 8 | 7 | 8 | 7 | 2017-07-07 | NULL | 2017-07-07
2017-07-07 | Support Function QA | 15247 | Arpitha Karividha | Test Case Design | Test Case Design | Test Case Design | Test Case Design | 8 | 8 | 16 | 8 | 16 | 2017-07-07 | NULL | 2017-07-07
2017-07-07 | SmartAid | 15781 | Priya Ingole | Test case Design | Test case Design | Update regression Log 7 July, 2017 | Updation of old test cases | 8 | 50 | 22 | 14 | 8 | 2017-07-07 | NULL | 2017-07-03
2017-07-08 | SmartAid | 11303 | Sandesh Upadhye | Test case Design | Test case Design | Update regression Log 7 July, 2017 | Updation of old test cases | 3 | 50 | 22 | 14 | 3 | 2017-07-08 | NULL | 2017-07-03
2017-07-08 | Support Function QA | 15247 | Arpitha Karividha | Test Case Execusion | Test Case Execusion | Test Case Execusion | Test Case Execusion | 4 | 8 | 36 | 8 | 36 | 2017-07-03 | NULL | 2017-07-07
2017-07-08 | SmartAid | 15781 | Priya Ingole | Test case Design | Test case Design | Update regression log 8-jul | Award Letter functionaality | 8 | 50 | 22 | 8 | 8 | 2017-07-08 | NULL | 2017-07-03
2017-07-09 | SmartAid | 15781 | Priya Ingole | Regression Log Updation | Regression Log Updation | Award , Award letter & Enterprise Test cases | Award , Award letter & Enterprise Test cases | 8 | 80 | 8 | 8 | 8 | 2017-07-09 | NULL | 2017-08-11
2017-07-10 | SmartAid | 8516 | Abhishek Dalal | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | 1 | 30 | 6 | 26 | 1 | 2017-07-10 | NULL | 2017-07-17
2017-07-10 | SmartAid | 8516 | Abhishek Dalal | Sprint wise test case updation | Sprint wise test cases updation | Sprint wise testcase updation | Sprint wise testcase updation | 7 | 100 | 7 | 16 | 7 | 2017-07-10 | NULL | 2017-07-20
2017-07-10 | SmartAid | 11303 | Sandesh Upadhye | Ticket Verification | Bug Verification | Smart Tuition LUCA & STND | LUCA & STND | 8 | 50 | 43 | 7 | 8 | 2017-07-10 | NULL | 2017-07-03
2017-07-10 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check 4. Taxanomy Changes | Sanity Testing -SP2 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | 2.3 | 15 | 10 | 15 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-10 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP2 | 1. IONToGo Mobile Feed monitoring on Prod 2. Daily Job monitoring (DEV, QA & PROD) for whole Week | 2.1 | 10 | 12 | 10 | 12 | 2017-07-11 | NULL | 2017-07-14
2017-07-10 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification -S2 | Data Verification | 2 | 10 | 10 | 10 | 10 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MAR ETL Mapping document task | 1. Mavis to MAR ETL Mapping document task 2. Defect Verification | Mavis to MAR ETL Mapping document task -SP2 | Mavis to MAR ETL Mapping document task | 1 | 5 | 4 | 5 | 4 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2(CRUD) | 4 | 16 | 16 | 16 | 8 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 12116 | Suvarna Bodkhe | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 2 | 20 | 13 | 20 | 7 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 12116 | Suvarna Bodkhe | Question And Answer | Question And Answer -W2 | Question And Answer | Question And Answer | 1.75 | 10 | 7 | 10 | 5 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 15247 | Arpitha Karividha | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2(CRUD) | 4 | 16 | 16 | 16 | 8 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 15247 | Arpitha Karividha | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 2 | 20 | 13 | 20 | 6 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | Support Function QA | 15247 | Arpitha Karividha | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | 2 | 14 | 7 | 14 | 2 | 2017-07-10 | NULL | 2017-07-14
2017-07-10 | SmartAid | 15781 | Priya Ingole | Test Case Execution | Test Case Execution | Happy Path Testing | Production for 3.32.2 Hotfix | 8 | 50 | 8 | 8 | 8 | 2017-07-10 | NULL | 2017-07-18
2017-07-11 | SmartTuition | 8516 | Abhishek Dalal | Ticket Verification | LUCA, STND, SHIELD etc | STND & LUCA | Ticket Verification | 6 | 120 | 47 | 14 | 6 | 2017-07-11 | NULL | 2017-08-11
2017-07-11 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | STND & LUCA | Ticket Verification | 8 | 120 | 47 | 14 | 8 | 2017-07-11 | NULL | 2017-08-11
2017-07-11 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check 4. Taxanomy Changes | Sanity Testing -SP2 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | 2 | 15 | 10 | 15 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-11 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP2 | 1. IONToGo Mobile Feed monitoring on Prod 2. Daily Job monitoring (DEV, QA & PROD) for whole Week | 2.3 | 10 | 12 | 10 | 12 | 2017-07-11 | NULL | 2017-07-14
2017-07-11 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification -S2 | Data Verification | 2 | 10 | 10 | 10 | 10 | 2017-07-10 | NULL | 2017-07-14
2017-07-11 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MAR ETL Mapping document task | 1. Mavis to MAR ETL Mapping document task 2. Defect Verification | Mavis to MAR ETL Mapping document task -SP2 | Mavis to MAR ETL Mapping document task | 1 | 5 | 4 | 5 | 4 | 2017-07-10 | NULL | 2017-07-14
2017-07-11 | Support Function QA | 12116 | Suvarna Bodkhe | System Testing-W2 | System Testing-W2 | System Testing-W2 | System Testing-W2 | 8 | 20 | 23 | 20 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-11 | Support Function QA | 15247 | Arpitha Karividha | System Testing-W2 | System Testing-W2 | System Testing-W2 | System Testing-W2 | 7 | 20 | 23 | 20 | 13 | 2017-07-12 | NULL | 2017-07-14
2017-07-11 | Support Function QA | 15247 | Arpitha Karividha | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 1 | 20 | 13 | 20 | 6 | 2017-07-10 | NULL | 2017-07-14
2017-07-11 | SmartTuition | 15781 | Priya Ingole | Test case Design | Regression Log or project wise testcases | Test case updation 13-July | Shield V2 | 8 | 150 | 10 | 3 | 10 | 2017-07-11 | NULL | 2017-08-11
2017-07-12 | SmartAid | 8516 | Abhishek Dalal | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Daily Scrum | Smart Aid Scrum | 1 | 30 | 6 | 1 | 2 | 2017-07-11 | NULL | 2017-07-17
2017-07-12 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Bug Verification | Smart Aid ticket verification 3.32.2 | NULL | 6 | 50 | 43 | 5 | 11 | 2017-07-07 | NULL | 2017-07-03
2017-07-12 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | Ticket Verification Dev - 12 July | Ticket Verification on Dev | 7 | 120 | 47 | 8 | 7 | 2017-07-12 | NULL | 2017-08-11
2017-07-12 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-12 | NULL | 2017-08-11
2017-07-12 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check 4. Taxanomy Changes | Sanity Testing -SP2 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | 3 | 15 | 10 | 15 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-12 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP2 | 1. IONToGo Mobile Feed monitoring on Prod 2. Daily Job monitoring (DEV, QA & PROD) for whole Week | 2 | 10 | 12 | 10 | 12 | 2017-07-11 | NULL | 2017-07-14
2017-07-12 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification -S2 | Data Verification | 2 | 10 | 10 | 10 | 10 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MAR ETL Mapping document task | 1. Mavis to MAR ETL Mapping document task 2. Defect Verification | Mavis to MAR ETL Mapping document task -SP2 | Mavis to MAR ETL Mapping document task | 1 | 5 | 4 | 5 | 4 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 12116 | Suvarna Bodkhe | System Testing-W2 | System Testing-W2 | System Testing-W2 | System Testing-W2 | 2 | 20 | 23 | 20 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 12116 | Suvarna Bodkhe | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 2 | 20 | 13 | 20 | 7 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2(CRUD) | 2.3 | 16 | 16 | 16 | 8 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 12116 | Suvarna Bodkhe | Question And Answer | Question And Answer -W2 | Question And Answer | Question And Answer | 1.3 | 10 | 7 | 10 | 5 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 15247 | Arpitha Karividha | System Testing-W2 | System Testing-W2 | System Testing-W2 | System Testing-W2 | 3 | 20 | 23 | 20 | 13 | 2017-07-12 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 15247 | Arpitha Karividha | Question And Answer | Question And Answer -W2 | Question And Answer | Question And Answer | 2 | 10 | 7 | 10 | 2 | 2017-07-12 | NULL | 2017-07-14
2017-07-12 | Support Function QA | 15247 | Arpitha Karividha | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 3 | 20 | 13 | 20 | 6 | 2017-07-10 | NULL | 2017-07-14
2017-07-12 | SmartTuition | 15781 | Priya Ingole | Test Case Execution | Production and Staging | Regression test for Shield V2 13July | on Production | 6 | 200 | 12 | 5 | 12 | 2017-07-12 | NULL | 2017-08-11
2017-07-13 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 1 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-13 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | Smart Aid tickets 13th July | on Staging | 3.25 | 80 | 32 | 3 | 3 | 2017-07-13 | NULL | 2017-07-21
2017-07-13 | SmartTuition | 8516 | Abhishek Dalal | Ticket Verification | LUCA, STND, SHIELD etc | LSR + STND 13-July | On Dev | 4.75 | 120 | 47 | 5 | 4 | 2017-07-13 | NULL | 2017-08-11
2017-07-13 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Bug Verification | Hot fix tickets on Production | Hotfix tickets | 6 | 50 | 43 | 7 | 6 | 2017-07-13 | NULL | 2017-07-03
2017-07-13 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | Rate Card - 13th July | on Construct | 6 | 120 | 47 | 6 | 6 | 2017-07-13 | NULL | 2017-08-11
2017-07-13 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | LSR + STND 13-July | On Dev | 1 | 120 | 47 | 5 | 1 | 2017-07-13 | NULL | 2017-08-11
2017-07-13 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-12 | NULL | 2017-08-11
2017-07-13 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check 4. Taxanomy Changes | Sanity Testing -SP2 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | 3 | 15 | 10 | 15 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-13 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification -S2 | Data Verification | 2 | 10 | 10 | 10 | 10 | 2017-07-10 | NULL | 2017-07-14
2017-07-13 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP2 | 1. IONToGo Mobile Feed monitoring on Prod 2. Daily Job monitoring (DEV, QA & PROD) for whole Week | 3 | 10 | 12 | 10 | 12 | 2017-07-11 | NULL | 2017-07-14
2017-07-13 | Support Function QA | 12116 | Suvarna Bodkhe | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 2 | 20 | 13 | 20 | 7 | 2017-07-10 | NULL | 2017-07-14
2017-07-13 | Support Function QA | 12116 | Suvarna Bodkhe | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | 3 | 14 | 7 | 14 | 5 | 2017-07-13 | NULL | 2017-07-14
2017-07-13 | Support Function QA | 12116 | Suvarna Bodkhe | Question And Answer | Question And Answer -W2 | Question And Answer | Question And Answer | 1 | 10 | 7 | 10 | 5 | 2017-07-10 | NULL | 2017-07-14
2017-07-13 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2(CRUD) | 2 | 16 | 16 | 16 | 8 | 2017-07-10 | NULL | 2017-07-14
2017-07-13 | SmartTuition | 15781 | Priya Ingole | Test case Design | Regression Log or project wise testcases | Test case updation 13-July | Shield V2 | 2.3 | 150 | 10 | 3 | 10 | 2017-07-11 | NULL | 2017-08-11
2017-07-14 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | Smart Aid Tickets 14 July | on Dev/Staging | 7.45 | 80 | 32 | 7 | 7 | 2017-07-14 | NULL | 2017-07-21
2017-07-14 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 0.75 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-14 | SmartAid | 8516 | Abhishek Dalal | Organizational Activities | Week 1 | Organizational Activities | Organizational Activities | 0.5 | 40 | 1 | 40 | 0 | 2017-07-14 | NULL | 2017-07-21
2017-07-14 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | LSR-Dev ticket verification 14 July | Dev | 1 | 120 | 47 | 2 | 1 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | LSR -turf ticket verification 14 July | NULL | 1 | 120 | 47 | 2 | 1 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | EIB-Construct ticket verification 14 July | NULL | 4 | 120 | 47 | 8 | 4 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-12 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | Luca -Dev ticket verification 14 July | NULL | 1 | 120 | 47 | 3 | 1 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MAR ETL Mapping document task | 1. Mavis to MAR ETL Mapping document task 2. Defect Verification | Mavis to MAR ETL Mapping document task -SP2 | Mavis to MAR ETL Mapping document task | 1 | 5 | 4 | 5 | 4 | 2017-07-10 | NULL | 2017-07-14
2017-07-14 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check 4. Taxanomy Changes | Sanity Testing -SP2 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | 0 | 15 | 10 | 15 | 10 | 2017-07-11 | NULL | 2017-07-14
2017-07-14 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP2 | 1. IONToGo Mobile Feed monitoring on Prod 2. Daily Job monitoring (DEV, QA & PROD) for whole Week | 3 | 10 | 12 | 10 | 12 | 2017-07-11 | NULL | 2017-07-14
2017-07-14 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification -S2 | Data Verification | 2 | 10 | 10 | 10 | 10 | 2017-07-10 | NULL | 2017-07-14
2017-07-14 | Support Function QA | 12116 | Suvarna Bodkhe | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | Test case design part 1-W2 | 2.3 | 14 | 7 | 14 | 5 | 2017-07-13 | NULL | 2017-07-14
2017-07-14 | Support Function QA | 12116 | Suvarna Bodkhe | Question And Answer | Question And Answer -W2 | Question And Answer | Question And Answer | 1.3 | 10 | 7 | 10 | 5 | 2017-07-10 | NULL | 2017-07-14
2017-07-14 | Support Function QA | 15247 | Arpitha Karividha | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2 | AdHoc Task-W2(CRUD) | 4 | 16 | 16 | 16 | 8 | 2017-07-10 | NULL | 2017-07-14
2017-07-14 | Support Function QA | 15247 | Arpitha Karividha | System Testing-W2 | System Testing-W2 | System Testing-W2 | System Testing-W2 | 3 | 20 | 23 | 20 | 13 | 2017-07-12 | NULL | 2017-07-14
2017-07-14 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | LSR-Dev ticket verification 14 July | Dev | 1 | 120 | 47 | 2 | 1 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartAid | 15781 | Priya Ingole | Organizational Activities | Week 1 | Organizational Activities | Organizational Activities | 1 | 40 | 1 | 40 | 1 | 2017-07-14 | NULL | 2017-07-21
2017-07-14 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | LSR -turf ticket verification 14 July | NULL | 1.3 | 120 | 47 | 2 | 1 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | EIB-Construct ticket verification 14 July | NULL | 4 | 120 | 47 | 8 | 4 | 2017-07-14 | NULL | 2017-08-11
2017-07-14 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | Luca -Dev ticket verification 14 July | NULL | 2 | 120 | 47 | 3 | 2 | 2017-07-14 | NULL | 2017-08-11
2017-07-17 | SmartTuition | 8516 | Abhishek Dalal | Ticket Verification | LUCA, STND, SHIELD etc | AMR, STND ticket Verification -17July | On Dev | 7.5 | 120 | 45 | 7 | 7 | 2017-07-17 | NULL | 2017-08-11
2017-07-17 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 0.5 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-17 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | Ticket verification - 17July | EIB-Rate Card, LSR-Dev , Lockout | 7.25 | 120 | 45 | 13 | 7 | 2017-07-17 | NULL | 2017-08-11
2017-07-17 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-SP3 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing-SP3 | Sanity Testing | 3 | 15 | 13 | 15 | 13 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification- SP3 | Data Verification- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring- SP3 | Monitoring- SP3 | 1.5 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP3 | 1.Mavis to MART ETL Mapping document-SP3 2. Defect Verification | 1.2 | 5 | 6 | 5 | 6 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Organisational Level Activities | 12116 | Suvarna Bodkhe | Leaves | Leaves | UnPlanned | NULL | 8 | 40000 | 1699 | 10000 | 8 | 2017-07-17 | NULL | 2017-12-31
2017-07-17 | Support Function QA | 15247 | Arpitha Karividha | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | 5 | 12 | 7 | 12 | 5 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Support Function QA | 15247 | Arpitha Karividha | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | 2 | 25 | 18 | 25 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | Support Function QA | 15247 | Arpitha Karividha | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 1 | 12 | 8 | 12 | 1 | 2017-07-17 | NULL | 2017-07-21
2017-07-17 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | Ticket verification - 17July | EIB-Rate Card, LSR-Dev , Lockout | 7.3 | 120 | 45 | 13 | 7 | 2017-07-17 | NULL | 2017-08-11
2017-07-18 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | Ticket Verification - 18-July | On Development | 7.75 | 80 | 32 | 6 | 7 | 2017-07-18 | NULL | 2017-07-21
2017-07-18 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 0.5 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-18 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | LSR + STND -18 July | On Turf + Dev | 6.45 | 120 | 45 | 14 | 6 | 2017-07-18 | NULL | 2017-08-11
2017-07-18 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-SP3 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing-SP3 | Sanity Testing | 3 | 15 | 13 | 15 | 13 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP3 | 1.Mavis to MART ETL Mapping document-SP3 2. Defect Verification | 1 | 5 | 6 | 5 | 6 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring- SP3 | Monitoring- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification- SP3 | Data Verification- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 12116 | Suvarna Bodkhe | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 2.15 | 12 | 8 | 12 | 7 | 2017-07-18 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 12116 | Suvarna Bodkhe | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | 1 | 4 | 51 | 4 | 51 | 2017-07-18 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 12116 | Suvarna Bodkhe | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | 3 | 25 | 18 | 25 | 9 | 2017-07-18 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | 1.3 | 12 | 7 | 12 | 2 | 2017-07-18 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 15247 | Arpitha Karividha | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | 7.3 | 25 | 18 | 25 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | Support Function QA | 15247 | Arpitha Karividha | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 0.3 | 12 | 8 | 12 | 1 | 2017-07-17 | NULL | 2017-07-21
2017-07-18 | SmartTuition | 15781 | Priya Ingole | Ticket Verification | LUCA, STND, SHIELD etc | LSR + STND -18 July | On Turf + Dev | 8 | 120 | 45 | 14 | 8 | 2017-07-18 | NULL | 2017-08-11
2017-07-19 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | Ticket Verification 19July | On Staging | 5.25 | 80 | 32 | 6 | 5 | 2017-07-19 | NULL | 2017-07-21
2017-07-19 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 0.75 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-19 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | 19 July - Rate Card Ticket Verification | Rate Card on Construct | 4 | 120 | 45 | 4 | 4 | 2017-07-19 | NULL | 2017-08-11
2017-07-19 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | 19 July - STND Ticket Verification | STND on Dev | 3 | 120 | 45 | 3 | 3 | 2017-07-19 | NULL | 2017-08-11
2017-07-19 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring- SP3 | Monitoring- SP3 | 2.3 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-19 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-SP3 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing-SP3 | Sanity Testing | 2 | 15 | 13 | 15 | 13 | 2017-07-17 | NULL | 2017-07-21
2017-07-19 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification- SP3 | Data Verification- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-19 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP3 | 1.Mavis to MART ETL Mapping document-SP3 2. Defect Verification | 1 | 5 | 6 | 5 | 6 | 2017-07-17 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 12116 | Suvarna Bodkhe | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | 1.15 | 5 | 5 | 5 | 3 | 2017-07-19 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 12116 | Suvarna Bodkhe | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 1.45 | 12 | 8 | 12 | 7 | 2017-07-18 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 12116 | Suvarna Bodkhe | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | Test case design _Sytorio-W3 | 50 | 4 | 51 | 4 | 51 | 2017-07-18 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | AdHoc Task and Review_Rework-W3 | 1 | 12 | 7 | 12 | 2 | 2017-07-18 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 12116 | Suvarna Bodkhe | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | 3 | 25 | 18 | 25 | 9 | 2017-07-18 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 15247 | Arpitha Karividha | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | 1 | 5 | 5 | 5 | 2 | 2017-07-19 | NULL | 2017-07-21
2017-07-19 | Support Function QA | 15247 | Arpitha Karividha | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | 7 | 22 | 22 | 22 | 22 | 2017-07-19 | NULL | 2017-07-21
2017-07-19 | SmartTuition | 15781 | Priya Ingole | Test Case Execution | Production and Staging | 19th and 20th July Rate card regression | EIB - rate card regresion on Construct | 8 | 200 | 47 | 16 | 15 | 2017-07-19 | NULL | 2017-08-11
2017-07-20 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 0.5 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-20 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | 20th July | Ticket Verification on Dev | 3.5 | 80 | 32 | 3 | 3 | 2017-07-20 | NULL | 2017-07-21
2017-07-20 | SmartAid | 8516 | Abhishek Dalal | Test case Design | Week 1 | Create 50 Families for send to smart | Create 50 Families for send to smart in Smart Aid and LUCA | 4 | 80 | 26 | 4 | 4 | 2017-07-20 | NULL | 2017-07-21
2017-07-20 | Organisational Level Activities | 11303 | Sandesh Upadhye | Leaves | Leaves | Planned Leave | NULL | 8 | 40000 | 1699 | 20000 | 8 | 2017-07-20 | NULL | 2017-12-31
2017-07-20 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP3 | 1.Mavis to MART ETL Mapping document-SP3 2. Defect Verification | 1 | 5 | 6 | 5 | 6 | 2017-07-17 | NULL | 2017-07-21
2017-07-20 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-SP3 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing-SP3 | Sanity Testing | 2.3 | 15 | 13 | 15 | 13 | 2017-07-17 | NULL | 2017-07-21
2017-07-20 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification- SP3 | Data Verification- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-20 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring- SP3 | Monitoring- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-20 | Support Function QA | 12116 | Suvarna Bodkhe | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 2.1 | 12 | 8 | 12 | 7 | 2017-07-18 | NULL | 2017-07-21
2017-07-20 | Support Function QA | 12116 | Suvarna Bodkhe | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | All Type Testing-W3 | 3 | 25 | 18 | 25 | 9 | 2017-07-18 | NULL | 2017-07-21
2017-07-20 | Support Function QA | 12116 | Suvarna Bodkhe | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | 2.3 | 5 | 5 | 5 | 3 | 2017-07-19 | NULL | 2017-07-21
2017-07-20 | Support Function QA | 15247 | Arpitha Karividha | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | 7 | 22 | 22 | 22 | 22 | 2017-07-19 | NULL | 2017-07-21
2017-07-20 | Support Function QA | 15247 | Arpitha Karividha | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | KT Sessions-W3 | 1 | 5 | 5 | 5 | 2 | 2017-07-19 | NULL | 2017-07-21
2017-07-20 | SmartTuition | 15781 | Priya Ingole | Test Case Execution | Production and Staging | 19th and 20th July Rate card regression | EIB - rate card regresion on Construct | 7 | 200 | 47 | 16 | 15 | 2017-07-19 | NULL | 2017-08-11
2017-07-21 | SmartAid | 8516 | Abhishek Dalal | Ticket Verification | Week 1 | 21 July Ticket Verification | On Dev | 7.75 | 80 | 32 | 7 | 7 | 2017-07-21 | NULL | 2017-07-21
2017-07-21 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 1 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-21 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-21 | NULL | 2017-08-11
2017-07-21 | SmartTuition | 11303 | Sandesh Upadhye | Test Case Execution | Production and Staging | 21 July EIB Regression | Construct | 4 | 200 | 47 | 4 | 4 | 2017-07-21 | NULL | 2017-08-11
2017-07-21 | SmartTuition | 11303 | Sandesh Upadhye | Ticket Verification | LUCA, STND, SHIELD etc | 21 July Ticket Verification | NULL | 3 | 120 | 45 | 3 | 3 | 2017-07-21 | NULL | 2017-08-11
2017-07-21 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-SP3 | 1. ION Portal Dashboards- Sanity Check on Prod 2. Global PNH/aHUS ION Dashboard Sanity Check on Prod 3. Executive Dashboard Prod Sanity Check | Sanity Testing-SP3 | Sanity Testing | 3 | 15 | 13 | 15 | 13 | 2017-07-17 | NULL | 2017-07-21
2017-07-21 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification- SP3 | Data Verification- SP3 | 1.3 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-21 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP3 | 1.Mavis to MART ETL Mapping document-SP3 2. Defect Verification | 2 | 5 | 6 | 5 | 6 | 2017-07-17 | NULL | 2017-07-21
2017-07-21 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring- SP3 | Monitoring- SP3 | 2 | 10 | 9 | 10 | 9 | 2017-07-17 | NULL | 2017-07-21
2017-07-21 | Support Function QA | 12116 | Suvarna Bodkhe | Defect raising and Retesting-W3 | Defect raising and defect Retesting-W3 | Defect raising and Retesting-W3 | Defect raising and Defect Retesting-W3 | 2 | 12 | 8 | 12 | 7 | 2017-07-18 | NULL | 2017-07-21
2017-07-21 | Support Function QA | 15247 | Arpitha Karividha | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | Syne_PMO-W3 | 8 | 22 | 22 | 22 | 22 | 2017-07-19 | NULL | 2017-07-21
2017-07-21 | SmartTuition | 15781 | Priya Ingole | Test case Design | Regression Log or project wise testcases | 21 July Rate Card Test cases updation | Test case updation | 8.3 | 150 | 15 | 8 | 8 | 2017-07-21 | NULL | 2017-08-11
2017-07-24 | SmartAid | 8516 | Abhishek Dalal | Test case Design | Week 1 | 24 July and 25 July Histroy tracking Test cases | Regression log update | 7.5 | 80 | 26 | 14 | 15 | 2017-07-24 | NULL | 2017-07-21
2017-07-24 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 1 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-24 | SmartTuition | 11303 | Sandesh Upadhye | Test Case Execution | Production and Staging | 24 July and 25 July EIB Regression | on Dev | 7 | 200 | 47 | 22 | 14 | 2017-07-24 | NULL | 2017-08-11
2017-07-24 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-21 | NULL | 2017-08-11
2017-07-24 | Organisational Level Activities | 11689 | Sagar Saibewar | Leaves | Leaves | Planned Leave | NULL | 8 | 40000 | 1699 | 20000 | 8 | 2017-07-24 | NULL | 2017-12-31
2017-07-24 | Support Function QA | 12116 | Suvarna Bodkhe | Defect Retesting and Defect raising | Defect Retesting and Defect raising-W2 | Defect Retesting and Defect raising | Defect Retesting and Defect raising | 1.3 | 20 | 13 | 20 | 7 | 2017-07-10 | NULL | 2017-07-14
2017-07-24 | Support Function QA | 12116 | Suvarna Bodkhe | KT sessions-W4 | KT sessions-W4 | KT sessions-W4 | KT sessions-W4 | 1.3 | 18 | 1 | 18 | 1 | 2017-07-24 | NULL | 2017-07-28
2017-07-24 | SmartTuition | 15781 | Priya Ingole | Test case Design | Regression Log or project wise testcases | 24 July EIB New tickets test case update | Test case design for new tickets | 7 | 150 | 15 | 8 | 7 | 2017-07-24 | NULL | 2017-08-11
2017-07-25 | SmartAid | 8516 | Abhishek Dalal | Test case Design | Week 1 | 24 July and 25 July Histroy tracking Test cases | Regression log update | 8 | 80 | 26 | 14 | 15 | 2017-07-24 | NULL | 2017-07-21
2017-07-25 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 1 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-25 | SmartTuition | 11303 | Sandesh Upadhye | Test Case Execution | Production and Staging | 24 July and 25 July EIB Regression | on Dev | 7 | 200 | 47 | 22 | 14 | 2017-07-24 | NULL | 2017-08-11
2017-07-25 | SmartTuition | 11303 | Sandesh Upadhye | Smart Tuition Daily Scrum | Scrum Call with Client | Smart Tuition Daily Scrum | Scrum Calla with client | 1 | 30 | 3 | 30 | 3 | 2017-07-21 | NULL | 2017-08-11
2017-07-25 | Alexion QA | 11689 | Sagar Saibewar | Sanity Testing-4 | Sanity Testing | Sanity Testing -SP4 | Sanity Testing -SP4 | 3 | 15 | 3 | 15 | 3 | 2017-07-25 | NULL | 2017-07-28
2017-07-25 | Alexion QA | 11689 | Sagar Saibewar | Data Verification | Data Verification | Data Verification-SP4 | Data Verification-SP4 | 2 | 10 | 2 | 10 | 2 | 2017-07-25 | NULL | 2017-07-28
2017-07-25 | Alexion QA | 11689 | Sagar Saibewar | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document | Mavis to MART ETL Mapping document-SP4 | Mavis to MART ETL Mapping document-SP4 | 0.5 | 5 | 0 | 5 | 0 | 2017-07-25 | NULL | 2017-07-28
2017-07-25 | Alexion QA | 11689 | Sagar Saibewar | Monitoring | Monitoring | Monitoring-SP4 | Monitoring-SP4 | 2 | 10 | 2 | 10 | 2 | 2017-07-25 | NULL | 2017-07-28
2017-07-25 | Support Function QA | 12116 | Suvarna Bodkhe | AdHoc Task and Review_Rework-W4 | AdHoc Task and Review_Rework-W4 | AdHoc Task and Review_Rework-W4 | AdHoc Task and Review_Rework-W4 | 30 | 2 | 30 | 2 | 30 | 2017-07-25 | NULL | 2017-07-28
2017-07-25 | SmartTuition | 15781 | Priya Ingole | Test Case Execution | Production and Staging | 24 July and 25 July EIB Regression | on Dev | 7.25 | 200 | 47 | 22 | 7 | 2017-07-25 | NULL | 2017-08-11
2017-07-26 | SmartAid | 8516 | Abhishek Dalal | Test case Design | Week 1 | 26 July Create 50 Families for send to smart | On Dev | 7.5 | 80 | 26 | 7 | 7 | 2017-07-26 | NULL | 2017-07-21
2017-07-26 | SmartAid | 8516 | Abhishek Dalal | Daily Scrum Meeting | Week 1 | Daily Scrum Meeting | Week 1 | 1 | 6 | 8 | 6 | 8 | 2017-07-13 | NULL | 2017-07-27
2017-07-26 | SmartTuition | 11303 | Sandesh Upadhye | Test Case Execution | Production and Staging | 26 July EIB AddHoc Testing | Dev | 7 | 200 | 47 | 15 | 7 | 2017-07-26 | NULL | 2017-08-11
2017-07-26 | Support Function QA | 12116 | Suvarna Bodkhe | All Type testing-W4 | All Type testing-W4 | All Type testing-W4 | All Type testing-W4 | 4.2 | 20 | 4 | 20 | 4 | 2017-07-26 | NULL | 2017-07-28